## ProductBacklog
Sprint name | Sprint number | User | Stories | Status | Priority | Deadline | Completion date | Problem | Problem Detail | Solution
Add treasure room | 1 | As a player I want to | explore more rooms | Done | 1 | 2021-05-18 | 2021-05-14 | Test case does not work => Fixed=>Test case implemented | Cannot run test file | Update project with Maven
Add armor | 2 | As a player I want to | interact with more items | Done | 1 | 2021-05-24 | 2021-05-15 | Test case does not work => Fixed=>Test case implemented | Cannot run test file | Update project with Maven
Add unlock room action | 3 | As a player I want to | unlock the locked room | Done | 2 | 2021-05-28 | 2021-05-21
Adding method comments/cleaning the code/ generate Javadoc | 4 | As a project manager/developer I want to | have clean and optimised code, , understandable documentation | Done | 3 | 2021-06-01 | 2021-06-01 | Cannot generate javadoc with private method => Accepted | Cannot generate javadoc for private methods | Accept
Provide additional information to user regarding room/item/game | 5 | As a player I want to | have more clarity | Done | 3 | 2021-06-04 | 2021-06-04

## TaskBoard
Sprint | Tasks | Person | Status | Problem
1 | List current rooms | MP,CC | Done
1 | Decide room to be added | MP,CC | Done
1 | Add the room | MP,CC | Done
1 | Test rooms | MP,CC | Done | Test file does not work, error code "No test executed" => Fixed
2 | List current items | MP,CC | Done
2 | Decide item to be added | MP,CC | Done
2 | Add the item | MP,CC | Done
2 | Test items | MP,CC | Done | Test file does not work, error code "No test executed" => Fixed
3 | List actions | MP,CC | Done
3 | Decide action to be added | MP,CC | Done
3 | Add Attack action | MP,CC | Done
3 | Test action | MP,CC | Done
4 | Design documentation | MP,CC | Done
4 | Add comment documentation | MP,CC | Done
4 | Generate documentation | MP,CC | Done | Cannot generate javadoc with private method => Accept
4 | Check documentation | MP,CC | Done
5 | Design instructions, descriptions | MP,CC | Done
5 | Add instructions, descriptions | MP,CC | Done