## ProductBacklog
Sprint name | Sprint number | Status | Priority | Deadline | Completion date | Problem
Adding more rooms | 1 | In Progress | 1 | 2021-05-18 | 2021-05-14 | Test case does not work
Add more items | 2 | Not Started | 1 | 2021-05-24 | 2021-05-15 | Test case does not work
Add Attack action | 3 | Not Started | 2 | 2021-05-28
Provide additional information to user regarding room/item | 4 | Not Started | 3 | 2021-06-01
Adding method comments/cleaning the code | 5 | Not Started | 3 | 2021-06-04

## TaskBoard
Sprint | Tasks | Person | Status | Problem
1 | List current rooms | MP,CC | Done
1 | Decide room to be added | MP,CC | Done
1 | Add the room | MP,CC | Done
1 | Test rooms | MP,CC | In Progress | Test file does not work, error code "No test executed"
2 | List current items | MP,CC | Done
2 | Decide item to be added | MP,CC | Done
2 | Add the item | MP,CC | Done
2 | Test items | MP,CC | In Progress | Test file does not work, error code "No test executed"
3 | List actions | MP,CC | In Progress
3 | Decide action to be added | MP,CC | In Progress
3 | Add Attack action | MP,CC | In Progress
3 | Test action | MP,CC | In Progress
4 | Design instructions, descriptions | MP,CC | Not Started
4 | Add instructions, descriptions | MP,CC | Not Started
4 | Test desciptions | MP,CC | Not Started
5 | Design documentation | MP,CC | Not Started
5 | Add comment documentation | MP,CC | Not Started
5 | Generate documentation | MP,CC | Not Started
5 | Check documentation | MP,CC | Not Started